## Sprint Setup
Sprint number | 1 | Team members
Sprint starting date | 2020-10-20 | Name | Main Role (BE, FE, SC, PO)
Sprint length | 14 | Pepito | BE
Sprint ending | 2020-11-03 | Pepita | FE
|  | Team Size | 2

## Sprint planning
Time management
Available working hours per team member | 8
Total amount of working hours | 16
Amount of hours remaining to work in User Stories | 16
User Stories
Which User Stories were estimated during the planning?
User Story | Story Points estimation (Complexity) | Task | Hours/Task | WHO ? | Was this User Story included in the sprint?
User story 1 | 13 | US1-Task1 | 3 | Pepita | Yes
|  | US1-Task2 | 4 |  | Yes
No
User story 2 | 3 | US2-Task1 | 7 |  | Yes
Amount of hours estimated to execute during this sprint |  |  | 14 | Breath, everything is OK
Questions
Which risks do we have during this sprint?
Which are the new technologies introduced in this sprint?
Which are the new methodologies introduced in this sprint?
How do we want to solve during this sprints the problems we had in the past sprint?

## Burndown chart
|  | 14 |  |  | 1
Day of sprint | Day of week | Is working day | Date | Remaining work | Target | Forecast | Forecast vs Target
1 | W | Yes | 2020-10-20 | 14 | 14 | 14 | 0
2 | T | Yes | 2020-10-21 | 14 | 13 | 14 | -1
3 | F | Yes | 2020-10-22 | 12 | 12 | 12 | 0
4 | S | Yes | 2020-10-23 | 10 | 11 | 10 | 1
5 | S | Yes | 2020-10-24 | 8 | 10 | 8 | 2
6 | M | Yes | 2020-10-25 | 6 | 9 | 6 | 3
7 | T | Yes | 2020-10-26 | 4 | 8 | 4 | 4
8 | W | Yes | 2020-10-27 | 2 | 7 | 2 | 5
9 | T | Yes | 2020-10-28 | 1 | 6 | 1 | 5
10 | F | Yes | 2020-10-29 | 1 | 5 | 1 | 4
11 | S | Yes | 2020-10-30 | 0 | 4 | 0 | 4
12 | S | Yes | 2020-10-31 | 0 | 3 | 0 | 3
13 | M | Yes | 2020-11-01 | 0 | 2 | 0 | 2
14 | T | Yes | 2020-11-02 | 0 | 1 | 0 | 1
15 | W | Yes | 2020-11-03 | 0 | 0 | 0 | 0
Breath, everything is ok
Formulas:
Date = [Date, row above]+1

## Standup Meeting Reporting
|  | Day 1 |  |  |  | Day 2 |  |  |  | Day 3 |  |  |  | Day 4 |  |  |  | Day 5 |  |  |  | Day 6 |  |  |  | Day 7 |  |  |  | Day 8 |  |  |  | Day 9 |  |  |  | Day 10 |  |  |  | Day 11 |  |  |  | Day 12 |  |  |  | Day 13 |  |  |  | Day 14 |  |  |  | Day 15
|  | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems | Attendance | Ahir vaig fer allò previst | Avui faré el que tenia previst | Problems
Pepito | BE | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
Pepita | FE | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
0 | 0 | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | No | No |  | No | No | No |  | No | No | No |  | No | No | No
0 | 0 | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
0 | 0 | No | No | No |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | No | No | No |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
0 | 0 | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes |  | Yes | Yes | Yes
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0

## Sprint Retrospective
User Stories
User Story - Task | Time estimation (Hours) | WHO | Was this User Story included in the sprint? | Which is the status of this User Story? | If it is not done, why? | How many time we had spend in this User Story?
US1-Task1 | 3 | Pepita | Yes | Done | Frontend sign up form not made | 14
US1-Task2 | 4 |  | Yes | Work in progress | Frontend not linked | 9
US2-Task1 | 7 |  | Yes | Done |  | 7
Estimated Time | 14
Actual Time | 30
Deviation | 16
Completion | 66.67%
Questions
Why we didn't complete all the user stories? |  | Because we made an optimistic time estimation of the time needed in the frontend tasks
Why we deviate from the estimated time? |  | Our FE team needed more time to develop and learn the skills requiered
What are we going to do in order to solve the time and completion deviations? |  | Try to improve the way we estimate the time needed
Which problems and oportunities do we found during the Sprint? |  | We can push a little more at the BE side.
TEAM SELF-ASSESMENT
My contribution to the team effort during thus sprint(1-5)
1- I almost had no contribution during this sprint
2- My contribution has been less than expected
3- My contribution has been according my capabilities and with the agreement of the team.
4- Contribution above expectations.
5- Outstanding contribution and suport to other team members

## Self-Assesment
TEAM SELF-ASSESMENT
| Team Members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7
STEP 1: Everybody introduces her/his self-assesment | Name 1
STEP 2: Everybody introduces the team assesment | Name 2
Name 3
Name 4
Name 5
Name 6
Name 7
My contribution to the team effort during this sprint(1-5)
1- I almost had no contribution during this sprint |  | [DIAGONAL---> Self-assesment]
2- My contribution has been less than expected |  | [Rest of the matrix ----> Team assesment]
3- My contribution has been according my capabilities and with the agreement of the team.
4- Contribution above expectations. |  |  | Columna Y: Notes rebudes per Y. Fila X: Notes que posa X a la resta del grup
5- Outstanding contribution and suport to other team members